## Sheet1
COSC 310 Project | Start Time: Jan 21th | End Time: Feb 6th
Task Name | Estimated Duration (hr) | Actual Duration (hr)
1. Planning & Designing | 12 | 10
1.1 GitHub Setup | 4 | 4
1.1.1 Repository Setup | 1 | 1
1.1.2 Project File Setup | 1 | 1
1.1.3 Learn Push, Pull, Branch | 2 | 2
1.2 Project Analysis | 5 | 3
1.2.1 Chatbot Examples | 1 | 1
1.2.2 Chatbot Type | 2 | 1
1.2.1 Chatbot Functionality | 2 | 1
1.3 Task Breakdown | 3 | 3
1.3.2 Chatbot Requrements (API) | 2 | 2
1.3.3 Determine Task For Each Member | 1 | 1
2. Development & Testing | 174 | 188
2.1 Code Implementation | 120 | 140
2.1.1 Code Individual | 100 | 140
2.2 Merge Code | 18 | 12
2.2.1 Combine Code | 12 | 8
2.2.2 Explaining Code To Each Other | 6 | 4
2.3 Testing The Code | 36 | 36
2.3.1 Code Testing | 36 | 36
3. Documentation & Maintenance Phase | 42 | 44
3.1 Code Review | 24 | 24
3.2 Detail Description | 18 | 20
3.2.1 Explain Method, Function work | 16 | 16
3.2.2 List of Limitations | 2 | 4
Total Project Time | 228 | 242